{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["工程量清单"],"read":"whole","date_system":"1900"}

{"sheet":"工程量清单","index":0,"n_rows":50,"n_cols":8,"rows_kept":50,"merged":[[0,0,0,7],[1,1,1,4],[45,0,45,7],[46,0,46,5],[47,0,47,5],[48,0,48,5],[49,0,49,5]]}
["工程量清单"]
["项目名称：","固原市海绵城市建设公园广场-古城墙遗址公园二期、三期项目-二期水电安装劳务工程"]
["序号","项目名称","项目特征","单位","工程数量","全费用综合单价（元）","合计（元）","备注"]
["一","A\\B\\C\\D\\E区电气工程",null,"",""]
[1,"1.名称:庭院灯\n2.型号:220V  45W \n3.规格:节能灯H=6.0                               4.灯基础:600*600*600mmC20混凝土","灯基础土方开挖、回填、基层素土夯实、基础支模浇筑、接线、灯具安装、调试等","套",361,null,null,"材料甲供"]
[2,"1.名称:草坪灯\n2.型号:220V  35W  \n3.规格:LED灯                                        4.灯基础:300*300*300mmC20混凝土","灯基础土方开挖、回填、基层素土夯实、基础支模浇筑、接线、灯具安装、调试等","套",166,null,null,"材料甲供"]
[3,"1.名称:嵌入式壁灯\n2.型号:220V  13W  \n3.规格:LED灯","预留孔洞清理、接线、灯具安装、调试等","套",149,null,null,"材料甲供"]
[4,"1.名称:埋地射灯\n2.型号:220V  18W \n3.规格:LED灯","灯基础土方开挖、回填、基层素土夯实、接线、灯具安装、调试等","套",12,null,null,"材料甲供"]
[5,"1.名称:配电箱AL1（7回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:1200*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[6,"1.名称:配电箱AL2（5回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:1200*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[7,"1.名称:配电箱AL3（4回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:900*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[8,"1.名称:配电箱AL4（4回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:900*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[9,"1.名称:配电箱AL5（5回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:1200*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[10,"1.名称:配电箱AL6（5回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:1200*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[11,"1.名称:配电箱AL7（1回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:900*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[12,"1.名称:配电箱AL8（6回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:1200*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[13,"1.名称:配电箱AL9（5回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:1200*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[14,"1.名称:配电箱AL10（3回路）\n2.型号、规格:按系统定制(IP66防水型）\n3.基础形式、材质、规格:900*600*300mmC20混凝土基础\n4.接线极材质、规格:50*5热镀锌角钢，长2.5m，间距5m\n5.接地线材质、规格:40*4热镀锌扁钢\n6.安装形式:落地安装\n7.包含独立接地装置调试","电箱基础土方开挖、回填、基层素土夯实、基础支模浇筑、开箱、清扫、检查、测位、划线、钻孔、装螺栓、本体安装、盘内整理、接线、接地、补漆","台","1",null,null,"材料甲供"]
[15,"1.名称:电力电缆\n2.型号:YJV\n3.规格:3X4mm2\n4.材质:铜芯\n5.敷设方式、部位:管内直埋敷设\n6.电压等级(kV):1KV","开盘、检查、架线盘、敷设、锯断、收线盘、测量绝缘电阻、临时封头、挂标牌","m",12402,null,null,"材料甲供"]
[16,"1.名称:电缆保护管\n2.材质:PVC\n3.规格:De32\n4.敷设方式:直埋","测位、断管、配管、固定、连接管件","m",12402,null,null,"材料甲供"]
[17,"1.土壤类别:一二类土\n2.人机配合开挖，深度1.0m","测位、划线、挖电缆沟、回填土、夯实","m3",5579.7]
["二","A\\B\\C\\D\\E区给水工程"]
[1,"1.材质及规格:聚乙烯PE管、De25 \n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、砂回填、水压试验等","m","12368",null,null,"材料甲供"]
[2,"1.材质及规格:聚乙烯PE管、De32 \n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、砂回填、水压试验等","m","3424",null,null,"材料甲供"]
[3,"1.材质及规格:聚乙烯PE管、De50\n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、砂回填、水压试验等","m","553",null,null,"材料甲供"]
[4,"1.材质及规格:聚乙烯PE管、De63\n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、砂回填、水压试验等","m","1438",null,null,"材料甲供"]
[5,"1.材质及规格:聚乙烯PE管、De75\n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、砂回填、水压试验等","m","809",null,null,"材料甲供"]
[6,"1.材质及规格:聚乙烯PE管、De90\n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、砂回填、水压试验等","m","1108",null,null,"材料甲供"]
[7,"1.材质及规格:聚乙烯PE管、De110\n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、砂回填、水压试验等","m","4523",null,null,"材料甲供"]
[8,"1.类型:球阀（取水阀）\n2.材质:聚乙烯\n3.规格、压力等级:De50\n4.连接形式:热熔连接","取水阀安装、调试","个","34",null,null,"材料甲供"]
[9,"1.喷头品种:摇臂式喷头\n2.射程:6.0m\n3.规格:De25","喷头安装、调试","个","2335",null,null,"材料甲供"]
[10,"1.材质及规格:聚乙烯PE管、De50 取水阀竖管\n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、水压试验等","m","48",null,null,"材料甲供"]
[11,"1.材质及规格:聚乙烯PE管、De25  喷头竖管\n2.压力等级：MPA≥1.0mpa\n3.连接形式:热熔连接\n4.铺设深度:1.0m\n5.管道检验及试验要求:按照国家标准进行压力实验","场内搬运、外观检查、切管、热熔、上管件、调直、水压试验等","m","2802",null,null,"材料甲供"]
[12,"阀门井，直径1200-1400mm,图集详见：05S502","砂浆拌合、砌砖、刮缝, 钢筋制安, 模板制安、拆除、清理, 混凝土浇筑、振捣、养护, 抹防水、防潮层, 井盖安装, 材料运输","座","62",null,null,"材料甲供"]
[13,"管沟土方，深度≥1.3m","1.挖土,将土堆放在沟、槽周边,清理机下余土\n2.清理边坡,工作面内人工排水等辅助性工作\n3.就地取土、回填土、按照设计及规范要求夯填土、清理 \n4.开挖完成后沟槽原土夯实","m3",25000]
[14,"1.名称:管道垫层\n2.垫层材料种类:3:7灰土\n3.厚度:300mm厚\n4.详见图集04S531-1-12","底层平整,拌合,分层铺设,找平压实等","m3","5813.52",null,null,"材料甲供"]
["三","A\\B\\C\\D\\E区排水工程"]
[1,"聚乙烯双壁波纹管De200","场内搬运、检查、管材清理及外观检查、切管、安装、闭水试验","m",2500,null,null,"材料甲供"]
[2,"聚乙烯双壁波纹管De300","场内搬运、检查、管材清理及外观检查、切管、安装、闭水试验","m",6000,null,null,"材料甲供"]
[3,"150厚中粗砂基础","按图纸要求回填","m3",{"$f":"E38*0.8*0.15+E39*0.9*0.15","v":1110},null,null,"材料甲供"]
[4,"管沟土方，深度≥1.05m","1.挖土,将土堆放在沟、槽周边,清理机下余土\n2.清理边坡,工作面内人工排水等辅助性工作\n3.就地取土、回填土、按照设计及规范要求夯填土、清理","m3",8500]
["八","其他"]
[1,"技工",null,"工日",100]
[2,"小工",null,"工日",100]
[null,"合计",{"$nulls":4},{"$f":"SUM(G5:G44)","v":{"v":0,"d":"0.00"}}]
["1.全费用综合单价：包含但不限于人工费（含人员加班费用）、甲供材下料、清点、卸车、验收、保管、施工、养护、清理施工后现场、垃圾清运、材料二次倒运费用（平均按500m以内考虑）、机械费及小型机具费用、赶工措施费用、技术服务费（测量放线等）、通讯费、交通费、食宿费、劳保用品费、相关保险费用、企业管理费、利润、措施费、规费、税金及政策性文件规定费用等所有费用。"]
["2、以上工程量均为暂定量，结算以现场实际发生工程量为准。"]
["3、材料损耗按宁夏园林定额2013损耗考核，超过定额损耗的，由乙方承当损失。"]
["4、以上报价按9%的增值税税金报价，签订合同时按实际税点调整合同单价。"]
["5、计量方式按《2013年工程量情况计量规范》的计量标准实行。"]